## Slide 1
Layout of MESA and experimental setups
Current status of realization
MESA schedule
MESA – a fully instrumented ERL project for nuclear and particle physics experiments
ERL Workshop 2022
October 3rd 2022
Florian Hug presenting work of the
MESA group
Partially supported by the European Union’s Horizon 2020 Research and Innovation programme under Grant Agreement No 101004730 (iFAST).

## Slide 2
MAMI is operating since >25 years at KPH
In 2012 funding of PRISMA cluster of excellence has been granted including a new accelerator project: Mainz Energy Recovery Superconducting Accelerator (MESA) to be built in the exisisting facility
In June 2015 DFG granted a research building to JGU „Center for Fundamental Physics (CFP)“ including an extension for MESA halls
MAMI and MESA at KPH Mainz

## Slide 3
Detailed informations on MESA experiments: Talk by Kurt Aulenbacher (presented by F. Hug) on Wednesday

## Slide 4
In June 2021
it was offically announced that full occupancy of CFP-1 will be possible in mid/end 2023
Representing a shift by almost
two years
Delay was anticipated early, Mitigation strategy est. 2019….
MESA Status

## Slide 5
Modulatorenhalle
Linac-tunnel
Most of instrumen
tation will be installed
in Modulator-halle
Beschleunigte Aufbaumassnahme MESA (BAM)
New building (CFP-1, hall-1)
Old building, halls-2-4

## Slide 6
Double sided recirculation design with normal-conducting injector and superconducting main linac
Two different modes of operation:
(1300 MHz CW beam) - EB-operation (P2/BDX experiment): polarized beam, up to 150 µA @ 155 MeV - ERL-operation (MAGIX experiment): (un)polarized beam, up to 1 (10) mA @ 105 MeV
Picture&lattice layout : D. Simon
Gun
MELBA
MAMBO
MEEC-1
MEEC-2
Recirculation arcs 1-3-5
Recirculation arcs 2-4
Ext. beamline
ERL loop
155 MeV dump
5 MeV dump
P2
MAGIX
MESA Accelerator Layout

## Slide 7
Picture &lattice layout : D. Simon
MELBA
MESA Accelerator Layout
Source and Beam preparation system:
MESA Low Energy Beam Apparatus (MELBA)
- Defines the quality of the MESA beam

## Slide 8
Lattice layout : PhD thesis D. Simon
MELBA
MAMBO
MESA Accelerator Layout
MESA injector linear accelerator:
Milli-AMpere-Booster (MAMBO)
In ERL mode, all beam power
(up to 50kW) comes from the injector:
MAMBO is the „powerhouse“
of MESA

## Slide 9
Old MELBA Test set-up
Operation with up to 150keV
beam and up to 10mA beam current
MELBA was dis-assembled and put in storage
due to start of hall renovation for MESA
PhD Theses completed
S. Friederich (2019)
R. Kempf (2020)
C. Matejcek (2021)
P. Heil (2021)
.
Transverse emittance
C. Matejcek et al. doi:10.18429/JACoW-IPAC2019-TUPGW028
Longitudinal emittance
P. Heil et al.
PHYS. REV. ACCEL. BEAMS
24, 042803 (2021)
Surface photovoltage in NEA GaAs at 10mA
S. Friederich et al .doi:10.18429/JACoW-IPAC2019-TUPGW028
MELBA Tests

## Slide 10
Photosource „STEAM“
(polarized beam)
Spin Manipulation
Circular
Chopper
High bunch charge/beam
current source
(unpolarized beam)
Double scattering
Mott polarimeter
To MAMBO
injector
f/2f buncher
cavities
Source/beam preparation (MELBA) layout

## Slide 11
Injector working principle
S. Friederich at al: IPAC 2021

## Slide 12
In a huge number of online meetings the arrangement of components has been planned
Several issues raised by results of test experiments and MAC suggestions adressed (improved corrector magnets, BPM‘s for P2, Spin manipulation. 5MeV polarimeter… )
„freezing“ & start assembly
in 2/2022
R. Heine: PHYSICAL REVIEW ACCELERATORS AND BEAMS 24, 011602 (2021)
MESA low energy beam apparatus (MELBA)
Milliampere Booster (MAMBO)
MARC-0 region
MELBA/MAMBO: final Accelerator Layout

## Slide 13
OPAL simulation results for complete injector
S. Friederich at al: IPAC 2021

## Slide 14
Injector Status today

## Slide 15
Impact of Pandemic on MESA construction- RF-vendors
74 kW 1300 MHz amplifier (CAD drawing)
Vendor: JEMA France (former SPE)
Amplifier batch: 1*74, 3*54, 4*15 kW
RF amplifiers & MAMBO Sections were ordered in 2019
…Based on existing protypes
Supplier for RF-amplifiers went bankrupt in 12/2020
New owner JEMA France continues contract
Successful SAT of 4*550 Watt basic module in 9/2021
Delivery of first (biggest) amplifier now scheduled for end 22
Auxiliary systems (LLRF, vacuum, diagnostics), expected to be
ready before amplifier delivery

## Slide 16
Picture/beam line&lattice layout : D. Simon
MELBA
MAMBO
MEEC-1
MEEC-2
Cryomodules
MESA ELBE-Enhanced Cryomodule (MEEC):
Superconducting RF-cavities provide large
energy gain on small footprint and enable
Energy-recovery-Linac (ERL)-operation

## Slide 17
3.5 meter
Specs: 25 MeV Energy gain at <40 Watt thermal loss at 2 Kelvin
SRF-System: MEEC-Cryomodules

## Slide 18
2015: 2 MEEC’s ordered at RI Research Instruments GmbH
Until 2017 SRF testing infrastructure became available at HIM
9/2018: First cryomodule does not meet specs at HIM  refurbishment by vendor,
3/2019: Second tested cryomodule achieves specs during test at HIM/Mainz
8/2020 :refurbished cryomodule tested and fulfills specs.
2K operation
PhD thesis Timo Stengler
See also: T. Stengler et al. Proc. SRF 2019
doi:10.18429/JACoW-SRF2019-TUP041
Production of 2 Cryomodules
Cryomodules miss dynamical specs slightly but fulfill static specs by wide margin  On average the Helium consumption is estimated to be less than anticipated.

## Slide 19
MESA/P2 construction- Cryogenics (main issues only…)
Upgrade of L280 plant will start May 2022
Plant can serve MESA + P2 solenoid
P2-refrigerator – cooling of Hydrogen target - needs separate cryoplant
Negotiations with companies specialized on cryogenic piping ongoing
(More about MESA SRF in a dedicated talk on Tuesday)
Coldbox with Compressor
(2*, “separate solution” )
SAC

## Slide 20
Picture/beam line&lattice layout : D. Simon
MARC1,3,5
Lattice ERL/EB mode
MARC2,4
EB-beamline
Erl-loop

## Slide 21
ERL-Lattice – not completely symmetrical due to enery (gain)
dependent focussing of RF-structures.
PhD theses Ch. Stoll and D. Simon
Lattice: ERL mode start to end simulation

## Slide 22
Optics symmetric with respect to the middle of the long straight section. a=0 in the middle of the return arc
Return arc is free of transverse and vertical dispersion
Longitudinal dispersion r56 can be adjusted by changing the gradients of the middle quadrupoles in the 45° sections
Total length of 1st return arc: ~45m difference in time-of-flight for beams of 15 MeV and 30 MeV: Dt=60.5 ps  28.3° in RF @ 1.3 GHz
Path length adjustment needed (2 cm minimum ≈ 35° RF-phase) for complete flexibility in beam energy (chicane or moveable magnets)
Recirculation arcs optics

## Slide 23
BBU investigation
PhD thesis Christian Stoll,
See also: C. Stoll and F. Hug: proceedings IPAC 2019 doi:10.18429/JACoW-IPAC2019-MOPGW025
Note:
Technical limitation: Heating
of HOM coupler in TESLA cavities.
(~1mA CW estimation, but needs to
be determined experimentally)
13mA BBU limit at Target
in 4pass configuration 2up/2down
(without countermeasures)
BBU simulations by Ch. Stoll /Thermal modelling T. Stengler

## Slide 24
MESA construction- Magnets
Magnet Basic parameters well known and not demanding
Task before tendering:
Determine lattice tolerance against field errors
 avoid unnecessary precision requirements
Tendering started September 2022
MARC 1-5
Spreader/recombiner
ERL-ARC (MAGIX)
EB-Line (P2)
MESA ERL Mode beta-functions
F. Hug/D. Simon/C. Stoll

## Slide 25
Summary
MESA is a fully instrumented ERL facility for nuclear and particle physics experiments
Construction of injecctor is ongoing, main accelerator construction will be started as soon as the new building is ready (Jan 2023)
Most critical components are tested already. „Uncritical“ components are in the process of tendering
First beams to at low energy (15-55 MeV, 1 Recirculation) to the experiments can be expected 2 years after building occupancy