## Slide 1: CBETA Technical Review
1.11 Systems Integration
January 31, 2017
Richard E. Gallagher

## Slide 2: January 2017 Layout

## Slide 3: 2019 Layout

## Slide 4: January 2017: 3 Major Move Actions

## Slide 5: East-RF Power System CBETA Beam-Stop goes here

## Slide 6: East-RF Power System Move
Since the system is essential to CESR-CHESS operations, a 2-part approach is necessary:
Re-route the RF waveguides to a new transmitter and modify controls
Re-create the East-RF system in the L0 Pit vacated by the CLEO Particle detector

## Slide 7: East-RF powered by different transmitter

## Slide 8: East RF move to L0 Pit

## Slide 9: East RF Move Schedule
January 2017: Start installing waveguide, cable tray, cables and related modification
August 2017: Power east SRF cavities with different transmitter (commissioning while CESR-CHESS is off-line)
October 2017: East RF Pit Transmitter on-line
November 2017: Remove East RF components to permit wall modifications (maybe sooner)

## Slide 10: Remove the Vacuum Lab Structure South beamline goes here

## Slide 11: Relocate Gun Development Lab to make room for Vacuum Lab move

## Slide 12: Reconfigure Cooling System: CESR-85F

## Slide 13: Reconfigure Cooling System: CESR-85F

## Slide 14: Schedule for CESR-85F modifications
June 2017: Install new platforms
July 2017: Move pumps and DI tanks
August 2017: Instrumentation and controls
September 2017: Fully operational

## Slide 15: Other Cooling Requirements
Gun, ICM, klystrons, and existing beamline components are cooled by DI water systems.
Little capacity left on existing DI water systems
Dump cooling will require 75-gpm
Beamline Halbach and Splitter magnet requirements are not final
Plan is to install new closed loop heat exchangers
Campus Chilled Water will be extended to high bay area, but need flow-temp-DI requirements

## Slide 16: Campus Chilled Water (CCW)

## Slide 17: Electrical Requirements

## Slide 18: Electrical Requirements
Final design specifications for:
  Magnet PS
  Beamline components
  Instrumentation and controls
  MLC SSA and pump skids
  Cable trays and wire routes
  Lighting and convenience outlets
  Vacuum chamber bake-out
  Air cooling (fans) and local ventilation
  Metering

## Slide 19: HVAC: temperature stability, humidity, air-flow and control

## Slide 20: Other Utilities and Services
IT hardware
Network capacities: wired and wireless
Compressed air
GN2
Survey and Reference system
Fire detection and alarm
Overhead crane access
Drainage
Potable water

## Slide 21: East Wall Modification

## Slide 22: East Wall Modifications

## Slide 23: East Wall Modification Schedule
February 2017: Finalize location and sizes
March 2017: Engineering review of concept
June 2017: Engineering design
August 2017: Contract bids and award
December 2017: Construction
January 2018: Start installation for Partial Arc Test

## Slide 24: Beamline System Integration Installation and Assembly

## Slide 25: Beamline System Integration Installation and Assembly Sequence
Section 00-IN Gun and ICM are installed and operational
Section 01-LA is the MLC relocation, and is in progress
Section 02-SX Northeast merger in place February 2018
The subsequent installations after the CHESS-U CESR work (November 2018)

## Slide 26: Beamline System Integration Installation and Assembly Sequence
Installation will be in a clock-wise sequence
Sections 03-FA to 09-RX will be generally duplicate efforts
  Alignment
  Vacuum connections
  Magnet power,
  Controls and instrumentation
  Cooling
  Electrical
  Compressed air
  GN2

## Slide 27: Beamline System Integration Installation and Assembly Sequence
Section 10-BS Beam stop will be a more involved installation:
  Alignment
  Magnets
  Beam pipes
  Vacuum connections
  Instrumentation
  Electrical
  Compressed air
  GN2
  Shielding

## Slide 28: Project Management
Operating accelerator and X-ray programs
  Requires detailed planning and scheduling for utility work and movement of components
Competition for shared resources
  Resource loaded schedules
  Common resource pool
  Weekly reviews to identify potential issues
Space Use
  Documented use with strict time limits

## Slide 29: 1.11 Systems Integration
The End