Date:		February 7, 2017

To:		File

From:		S. Peggs

Subject:	Response to recommendations from the Directors Review (July 27, 2016)

See https://indico.classe.cornell.edu/event/40/

Technical design:  “Is the overall technical design conceptually sound and likely to meet the project’s technical performance requirements? Does the project’s planning include a viable path to arriving at a detailed technical plan on the necessary time frame?”

- The magnet design should be completed with high priority and the in-house production of a first article should be performed with high priority in order to validate the feasibility of this most critical cost and schedule item.

Magnet designs (both FFAG & Splitter) are close to completion.  Prototype girder production (FFAG) is very high priority in support of Technical Milestones 2 & 3 (“Prototype girder assembled”, and “Magnet production approved”).

- It is critical that the last major questions for the technical plan (e.g. finalizing magnet specifications) be brought to a rapid conclusion so that a defensible cost estimate can be provided on the 2-month timescale.

Magnet specifications are essentially complete.  FFAG and Splitter cost estimates are already mature, although further value engineering is being pursued, for example with regard to the Splitter magnets and tables.

- Every effort should be made to freeze the technical plan by mid-August to ensure that sufficient time is provided to complete and thoroughly review the implications of the final cost estimate.

A baseline design exists and is frozen, i.e. the 161126 lattice (November 2016) that is described in the Design Report (January 2017).  The cost implications are well understood, notwithstanding ongoing fine-tuning efforts that will fully accommodate the Halbach magnet change that was made in late December.

- Include as separate WBS level 2 items: a) Controls, b) System Integration and pre-commissioning.

Done: “1.8 Controls” and “1.11 System Integration”.

- Consider including beam size measurements for separate passes in the baseline. Investigate a possibility of developing kicker + screen system in mergers.

We have studied this issue and do not believe that such a system is cost-effective within the constraints of a very tight budget.  Not included in the Instrumentation cost estimate.  Beam size measurements are possible at 6 MeV in the diagnostics beamline.  Beam viewers will be used in each splitter line for size measurements.

- Work out fall-back scenarios for delays in schedule / cost creep. In the case of delays with magnet / girders a fall-back scenario (focused on demonstration 1st turn + recovery in time) could include: a) reducing scope of mergers and b) substituting long beam transport line by a set of sparse magnets suitable for matching optics functions on both ends.

First turn beam and four-turn installation are both well-established parts of the NYSERDA contractual deliverables.  Therefore we are very limited in our ability to a) reduce the scope of the splitters [mergers].  The baseline design that we have established does not include b) sparse magnet for matching optics at both ends.

Project Scope: “Is a plan in place to establish the project’s scope and specifications sufficiently well to support detailed cost and schedule estimates? Are the scope apportionment and deliverables that are split between BNL and Cornell clearly established and well defined?”

- Scope contingency must be identified, with assigned costs, decision branch points and technical impact included, and be ready to present at the September review.

We are very limited in our ability to reduce scope, within the definitions of the current NYSERDA contract.  It is desirable to clarify the four-pass beam commissioning deliverable with respect to project completion (and KPPs and UPPs), for example by minor editing of Technical Milestones 11 and 12.  This may be possible as a secondary goal in a likely contract modification to specify the use of Halbach (and not hybrid) magnets in the FFAG arcs.

- The project team should continue to define WBS below level three. When developing WBS at the lower levels, the team should clearly define the institution – either BNL or CU -- that each WBS element is uniquely assigned to in order to ensure good cost control and scope capture in project development and execution.

WBS development below L3 is mature, but continues, with clear institutional separation.

- An “integration” L2 activity should be inserted to ensure that all activities and costs associated with integrated assembly of the full machine are captured.

Done: “1.11 System Integration”.

- The Go/No Go decision points requested by NYSERDA should be more thoroughly defined with clear statements of the performance issues that are addressed.

More thorough and clear technical definitions of Go/No-Go goals benefit the project.  They continue be developed, for example as the technical risks that can be addressed and retired become better understood.  There is no indication that NYSERDA themselves require more thorough definitions.

Cost and Schedule: “Are the cost and schedule estimates credible and realistic for this stage of the project? Is a realistic plan in place to develop detailed estimates on the required time scale?”

- The project should be segmented into deliverables of appropriate scale, and a clear BoE developed for each deliverable. This will facilitate reviewing the project as it seeks approval for construction.

BoE documentation exists for each Level 2 item, some of which is being presented at the February 6&7 (2017) Cost and Schedule review, in preparation for construction approval.

- The team should consider developing a WBS that can capture all integration costs, and also assign a responsible person to the integration effort.

The current WBS 1.11 (System Integration) captures these costs, and its Level 2 lead is responsible for the integration effort within the scope of WBS 1.11.

- Begin constructing a resource loaded project file in an appropriate tool (i.e., MS Project or PRIMAVERA) as soon as possible.

We are actively developing an MS Project file, with a high priority.

- Expedite the design of the magnets to the extent that a reasonably reliable cost for the magnet system can be determined with highest priority.

Done.

- An assumptions document describing general estimating assumptions, and particularly the manpower availability assumptions for construction and commissioning, should be prepared.

Such an assumptions document remains to be developed.

Management and ES&H: “Is the project being appropriately managed at this stage? Will the management model properly support the project goals? Have the anticipated roles and responsibilities of both the institutions and the project principals been adequately defined and understood by all parties? Are plans in place to populate a full project team to the necessary WBS level? Is there sufficient Laboratory and University support to produce a credible technical, cost and schedule baseline on the needed time scales? Is a plan in place to develop a risk analysis and mitigation strategies? Are the plans for establishing ES&H aspects of the project sufficient given the project’s current stage of development?”

- Create a detailed timeline (milestones) for how the next generation cost and schedule will be developed, and socialize it with the Level 2 and other managers so that they understand what they will be expected to provide over the coming weeks. In order to be useful and effective, this should be generated within the next few working days.

The socialization of the Level 2 and other managers continues – and is a two-way street.  The next step is to manage mutual expectations in the generation of a robust and useful project schedule.

- Reconsider the roles and responsibilities in the PMP, particularly those in the Project Office, in a manner that takes full consideration of the flow of funds and institutional responsibilities.

The PMP revision of January 2017 better defines individual and institutional responsibilities.

- A clearer definition of how project reporting will be integrated across the institutions should be developed. The project reporting structure and the project tracking/reporting plans at BNL and Cornell should be reviewed to ensure that all reporting needs are satisfied.

Project reporting to NYSERDA is becoming well defined, for example with the imminent delivery of the first Quarterly Report on February 15, and with the recent establishment of Monthly Reporting.  Project tracking and reporting plans are under joint development by BNL and Cornell, and is being presented at the Cost & Schedule review (February 2017).

Documentation: “Are plans in place to produce the needed documentation in time for approval of a construction start in October 2016?”

- Formulate the needs for further support to bring the project plans and documentation to a conclusion by September.

The NYSERDA funding start date was October 31, 2016.  On January 31 2017 the project achieved Technical Milestone 1 (“Engineering design documentation complete”) by virtue of the Technical Review, which reported in part that “The engineering design is sufficiently mature to warrant the start of construction activities”.